## Delivery profiles
| Princes Risborough Expansion Area | [5 empty] | Housing Delivery Profile
[7 empty] | Within plan period | [14 empty] | Beyond plan period
[7 empty] | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | Total
| Ashill |  |  |  | 96 |  | Within plan period 2018/19: 16; Within plan period 2019/20: 40; Within plan period 2020/21: 40 | 96
| Station Site |  |  |  | 45 |  | Within plan period 2025/26: 20; Within plan period 2026/27: 25 | 45
| Poppy Road |  |  |  | 58 |  | Within plan period 2028/29: 29; Within plan period 2029/30: 29 | 58
| Bloor Homes |  |  |  | 853 | [5 empty] | 20 | 75 | 75 | 75 | 75 | 63 | 40 | 60 | 75 | 75 | 75 | 75 | 70 |  |  | 853
| Halsbury |  |  |  | 428 |  | Within plan period 2024/25: 50; Within plan period 2025/26: 50; Within plan period 2026/27: 50; Within plan period 2027/28: 50; Within plan period 2028/29: 50; Within plan period 2029/30: 50; Within plan period 2030/31: 50; Within plan period 2031/32: 50; Within plan period 2032/33: 28 | 428
| Persimmon |  |  |  | 363 |  | Within plan period 2024/25: 40; Within plan period 2025/26: 50; Within plan period 2026/27: 50; Within plan period 2027/28: 50; Within plan period 2028/29: 50; Within plan period 2029/30: 50; Within plan period 2030/31: 50; Within plan period 2031/32: 23 | 363
| Wates |  |  |  | 147 |  | Within plan period 2026/27: 25; Within plan period 2027/28: 40; Within plan period 2028/29: 40; Within plan period 2029/30: 42 | 147
| Taylor Wimpey |  |  |  | 254 |  | Within plan period 2026/27: 30; Within plan period 2027/28: 50; Within plan period 2028/29: 50; Within plan period 2029/30: 50; Within plan period 2030/31: 50; Within plan period 2031/32: 24 | 254
| Eyre |  |  |  | 64 |  | Within plan period 2028/29: 30; Within plan period 2029/30: 30; Within plan period 2030/31: 4 | 64
| Screech |  |  |  | 27 |  | Within plan period 2030/31: 13; Within plan period 2031/32: 14 | 27
| Skeet/Broadway/Luck |  |  |  | 25 |  | Within plan period 2030/31: 13; Within plan period 2031/32: 12 | 25
| Quilter |  |  |  | 93 |  | Within plan period 2030/31: 10; Within plan period 2031/32: 30; Within plan period 2032/33: 30; Beyond plan period 2033/34: 23 | 93
2453
| Total Annual (incl. 48% affordable) |  |  |  | 2453 |  | 16 | 40 | 40 | 0 | 20 | 75 | 165 | 195 | 255 | 253 | 289 | 311 | 265 | 228 | 133 | 98 | 70 |  | TOTALS
| Cumulative | [5 empty] | 16 | 56 | 96 | 96 | 116 | 191 | 356 | 551 | 806 | 1059 | 1348 | 1659 | 1924 | 2152 | 2285 | 2383 | 2453 |  | 2453 | TOTAL Area of Comprehensive Development
| Cumulative excluding Ashill | [5 empty] | 0 | 0 | 0 | 0 | 20 | 95 | 260 | 455 | 710 | 963 | 1252 | 1563 | 1828 | 2056 | 2189 | 2287 | 2357 |  | 2357 | Without Ashill | HIF (GFA) | used to be 2383
| (Main PREA only) | [5 empty] | Beyond plan period 2036/37: 2350 | Main Expansion
Infrastructure Delivery Profile
Programme
Programme | Cost Element | Delivered By | Funding | Capital (£) | Maintenance (£) | Total (£) | Prior Years | Prior Years | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37
Highways | Relief Road Phase 1 (SRL) | TBC- see appendix 1 | HIF/ developers | 31452868 |  | 31452868 |  | 478924 | 2020/21: 1686113; 2021/22: 1235985; 2022/23: 5512204; 2023/24: 19690694; 2024/25: 2077848; 2025/26: 771100
Highways | Relief Road Phase 3 Grove Lane | Developers | Developers | 17949578 |  | 17949578 |  |  | 2024/25: 624365; 2025/26: 849257; 2026/27: 2119311; 2027/28: 6790311; 2028/29: 7416334; 2029/30: 150000
Highways | Relief Road Phase 3 Lower Icknield Way | Developers | Developers | 18891158 |  | 18891158 |  |  | 2024/25: 18000; 2025/26: 525825; 2026/27: 849157; 2027/28: 1725055; 2028/29: 8427705; 2029/30: 7327416; 2030/31: 18000
Highways | Relief Road Phase 3 Culverton link | Developers | Developers | 7032210 |  | 7032210 |  | 0 | 2020/21: 0; 2024/25: 267280; 2025/26: 351644; 2026/27: 558144; 2027/28: 3159878; 2028/29: 2674764; 2029/30: 20500
0
Highways | Mill Lane and Askett area Improvements | Developers/BC | Developers | 2040000 |  | 2040000 |  |  | 2022/23: 1020000; 2028/29: 1020000
0
Highways | Sportsman' Roundabout | Developers | Developers | 998020.02 |  | 998020.02 |  |  | 2025/26: 998020.02
0
Highways | A4010 Traffic calming | Bucks Council | s106 | 5100000 |  | 5100000 |  |  | 2029/30: 2550000; 2030/31: 2550000
0
Rail | Underpass | Developers/NR | Developers | 3916826 |  | 3916826 |  |  | 2025/26: 3916826
0
Rail | Stepped footbridge | Developers | Developers | 1530000 |  | 1530000 |  |  | 2026/27: 1530000
0
Education | 3.9 * 2FE primary schools | Bucks Council | s106 | 24560193.9835 |  | 24560193.9835 |  | 0 | 0 | 0 | 208402.16 | 781508.08 | 1719317.78 | 2031921.01 | 2657127.48 | 2636287.26 | 3011411.14 | 3240653.51 | 2761328.56 | 2375784.57 | 1385874.33 | 1021170.56 | 729407.5435 | 0 | 0
Recreation | SOS1 Allotments | Developers | Developers/ s106 | 178500 | 89250 | 267750 |  |  | 2029/30: 178500; 2030/31: 25500; 2032/33: 40800; 2034/35: 22950
Recreation | SOS2 3 Sports Pitches | Developers | Developers/ s106 | 290700 | 805800 | 1096500 |  |  | 2025/26: 290700; 2026/27: 204000; 2028/29: 204000; 2030/31: 193800; 2032/33: 102000; 2034/35: 102000
Recreation | SOS1 1 Rugby Pitch | Developers | Developers/ s106 | 137700 | 382500 | 520200 |  |  | 2030/31: 137700; 2031/32: 204000; 2034/35: 178500
Recreation | SOS2 1 MUGA | Developers | Developers/ s106 | 153000 | 95880 | 248880 |  |  | 2026/27: 153000; 2027/28: 35700; 2029/30: 20400; 2031/32: 20400; 2034/35: 19380
Recreation | SOS2 3G Multi-sports | Developers | Developers/ s106 | 984300 | 122400 | 1106700 |  |  | 2026/27: 984300; 2027/28: 30600; 2029/30: 30600; 2031/32: 30600; 2034/35: 30600
Recreation | SOS2 3G Hockey | Developers | Developers/ s106 | 912900 | 112200 | 1025100 |  |  | 2027/28: 912900; 2028/29: 35700; 2030/31: 25500; 2032/33: 25500; 2034/35: 25500
Recreation | SOS2 4 tennis courts | Developers | Developers/ s106 | 372300 | 58140 | 430440 |  |  | 2029/30: 372300; 2030/31: 20400; 2032/33: 20400; 2034/35: 17340
Recreation | SOS2 Hub Mill Lane | Developers | Developers/ s106 | 759900 | 228480 | 988380 |  |  | 2025/26: 759900; 2026/27: 51000; 2028/29: 51000; 2030/31: 51000; 2032/33: 40800; 2034/35: 34680
Recreation | SOS1 Hub - Lower Icknield Way | Developers | Developers/ s106 | 642600 | 192780 | 835380 |  |  | 2029/30: 642600; 2030/31: 76500; 2032/33: 76500; 2034/35: 39780
Recreation | 2 NEAPS | Developers | Developers/ s106 | 510000 | 382500 | 892500 |  |  | 2024/25: 255000; 2025/26: 102000; 2026/27: 102000; 2028/29: 255000; 2029/30: 102000; 2030/31: 76500
Recreation | 5 LEAPS | Developers | Developers/ s106 | 382500 | 510000 | 892500 |  |  | 2023/24: 76500; 2024/25: 102000; 2025/26: 102000; 2026/27: 76500; 2027/28: 102000; 2028/29: 76500; 2029/30: 102000; 2030/31: 76500; 2031/32: 102000; 2032/33: 76500
Transport | Footpaths and cycling networks improvements (offsite) | Developers / BC | s.106 | 2040000 |  | 2040000 |  |  | 2030/31: 1020000; 2031/32: 1020000
Transport | Bus Provision | Bucks Council | s.106 | 1143236.5931 |  | 1143236.5931 |  |  | 2028/29: 228647.3186; 2029/30: 228647.3186; 2030/31: 228647.3186; 2031/32: 228647.3186; 2032/33: 228647.3186
Land | 3rd Party Land and Rights | Developer/BC | developers /s106 | 350000 |  | 350000 |  |  | 2024/25: 350000
Land | 3rd Party Land and Rights (Phase 3) | Developer/BC | developers /s106 | 2276502 |  | 2276502 |  |  | 2025/26: 1926502; 2028/29: 350000
Land | Part 1 Compensation | Developer/BC | developers /s106 | 342583 |  | 342583 |  |  | 2029/30: 171291.5; 2030/31: 171291.5
Admin | Council PM costs and costs associated with land acquisition | Bucks Council | s.106 | 800000 |  | 800000 |  |  | 2021/22: 100000; 2022/23: 200000; 2023/24: 200000; 2024/25: 200000; 2025/26: 100000
Health | Capacity for additional patients | Developer | s.106 | 750000 |  | 750000 |  |  | 2028/29: 750000
Land | Bradbury Equalisation | Developer | Developers | 494220 |  | 494220 |  |  | 2029/30: 494220
Land | Gladman Equalisation | Developer | Developers | 1334394 |  | 1334394 |  |  | 2025/26: 1334394
Land | Mrs Meech Equalisation | Developer | Developers | 395376 |  | 395376 |  |  | 2025/26: 395376
0
0
TOTAL | [5 empty] | 131701495.6007 |  | 478924 | 1686113 | 1335985 | 6940606.16 | 20748702.08 | 5613810.78 | 14455465.03 | 9284539.4798 | 15392731.2643 | 24501061.4586 | 15631128.3286 | 7432667.3786 | 3981431.8886 | 1997021.6486 | 1021170.56 | 1200137.5435 | 0 | 0 | 0
Years | [6 empty] | Prior Years | Prior Years | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/36
Separate allowance of £22,902,713 has been made in developers on-site contruction costs for phase 2.

## Housing Delivery graph
2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37
16 | 40 | 40 | 0 | 20 | 75 | 165 | 195 | 255 | 253 | 289 | 311 | 265 | 228 | 133 | 98 | 70