## Summary of Infrastructure
| Timings | Housing Numbers
| Indicative Years | Housing Numbers Delivery (cumulative) | Primary Education | Play | Strategic Open Spaces including Sports | Bus Services | Footpath and cycling networks | Relief Road within development | Local Centre | Local Open Spaces | Allotments | SuDS | Secondary Education | Culverton Link | Relief Road - A4010/Pict Lane/Summerleys Road (Southern Road Links) | Sportsman roundabout | Relief Road Lower Icknield Way and Grove Lane/A4010 | Relief Road Lower Icknield Way and Grove Lane/A4010 | Community and Health | Railway underpass to Wades Park and footbridge | Green infrastructure | A4010 improvements | Mill Lane / Askett Area | Town Centre Car Parking and Public Realm
Summary of Provision |  |  | 2 primary schools to be provided, one in each major phase of development | Provision of LEAPS and NEAPS within neighbourhoods | Provision of two sports hubs SOS1 off Lower Icknield Way and SOS2 off Mill Lane | Provision of new service through PREA + consider taxi-bus | Network of routes established through phased development | Phased alonsgide housing delivery | Comprise retail units totalling 300-400 m2 and new business units totalling 500 m2 | Local Plan policy for local public open space: 1.15 hectares of local space per 1,000 pop | Provision of allotments at SOS1 | Locationally specific - details of what is required, when and where depend on strategic drainage study | Pro-rata contribution per dwelling required | New road link between A4010 to Picts Lane | Southern access from A4010 via improvements to network plus Summerleys Road railway bridge improvements and include Sumitomo site. | Key junction improvement Lower Icknield Way/ Longwick Road to asist with provision of network capacity unless via S278 agreement | Northern access from A4010 including new railway bridge and junction with A4010 | B4009 improvements | Additional primary care facilities/ capacity | Required to ensure integration with PR Town Centre and existing communities, and encourage sustainable travel | Provision to include GI enhancements including Crowbrook Corridor for wildlife and people | A4010 traffic management strategy - reducing road speed and encourage use of Relief Road | Traffic calming measures including shuttle-working under railway bridge | Town centre car parking and public realm improvements
Funding Source |  |  | S106 | Developers | Developers | Developers / S106 | Developers / S106 | Developers | Developers | Developers | Developers | Developers | Community Infrastructure Levy | Developers | Developers / Homes England | Developers / S278 | Developers / S278 | Developers / S278 | Developers / S106* | Developers | Developers / S106 | S106 | Developers / S278 | Community Infrastructure Levy
DELIVERY LEAD |  |  | Buckinghamshire Council | Developers | Developers | Buckinghamshire Council | Developers / Buckinghamshire Council | Developers | Developers | Developers | Developers | Developers | Buckinghamshire Council | Developers | Developers / Buckinghamshire Council / Network Rail - See Note 2 | Developers | Developers / Network Rail | Developers | CCG/Surgery | Developers / Network Rail | Developers | Buckinghamshire Council | Developers | Buckinghamshire Council / Princes Risborough Town Council
Phase 1 | 2018/2019 to 2027/2028 | 524 | Contributions to primary school places | 1 LEAP |  |  |  | Do minimum network improvements, delivery of the southern road links including Station Approach junction |  | Provision as part of development phase |  | As required to service Phase 1 housing schemes | Contributions made as part of housing delivery |  | Completion of southern access including through Sumitomo site by Autumn 2024 |  |  |  |  | Footbridge provided towards end of phase 1 | Provision made as part of development phase |  | Mill Lane / Askett area highways improvements
Phase 2 | 2024/25 - 2028/29 | 1206 | Contributions to primary school places After 50+96 homes land for the first school to be transferred First new Primary School Required after 349+96 homes By 1000+96 homes land for the second primary school to be transferred | I NEAP 2 LEAPS | Sports Hub Mill Lane; 3 G sports pitch, 3G hockey pitch, 3 full size sports pitches, 1 MUGA |  | Provision as part of development | By 241 homes delivery of road from Sumitomo to land north of Crowbrook corridor west of Longwick road |  | Provision as part of development phase |  | As required to service Phase 2 housing schemes | Contributions made as part of housing delivery Potential for increased capacity in the place planning area |  |  | Completion required by c. 690 homes |  |  | Contributions made as part of housing delivery | Wades Park Underpass after 150 homes in phase 2 and stepped railway bridge | Provision made as part of development phase |  | Mill Lane / Askett area traffic calming | Provision of town centre improvements not linked to A4010 package
Phase 3 | 2028/29 - 2034/35 | 2453 | Contributions to primary school places Second Primary School after c.1300 + 96 homes | 1 NEAP 2 LEAPS | Sports Hub Lower Icknield Way (SOS1) including rugby pitch + 4 tennis courts at SOS2 | Bus service through PREA | Provision as part of development |  | Local Centre | Provision as part of development phase | Allotments | As required to service Phase 3 housing schemes | Contributions made as part of housing delivery Potential for increased capacity in the place planning area | Road Link required by c. 1395 homes |  |  | Grove Lane bridge and junction required by c.1395 homes | by c. 1680 homes delivery of B4009 widening | Contributions made as part of housing delivery |  | Provision made as part of development phase | By 2140 homes delivery of A4010 package |  | Provision
Note 1: Since 1 April 2020, the functions of Wycombe District Council and Buckinghamshire County Council have been brought together in a single Unitary Council: Buckinghamshire Council.
Note 2: Buckinghamshire Council's role as delivery lead for the Southern Road Links is dependent on full (external) funding being secured for the Council to deliver this.
* Additional funding sources to be considered if required.