## VALP allocations
VALP ALLOCATIONS - BUILD OUT RATES
|  | Status at adoption | Projection or completion | 10/11 | 11/12 | 12/13 | 13/14 | 14/15 | 15/16 | 16/17 | 17/18 | 18/19 | 19/20 | 20/21 | 21/22 | 22/23 | 23/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | Site Totals
D-AGT1 | South Aylesbury (Between Lower Road and Wendover Road) |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2024/25: 75; 2025/26: 100; 2026/27: 150; 2027/28: 150; 2028/29: 150; 2029/30: 130; 2030/31: 120
| Land off Lower Road, Stoke Mandeville (132 dwellings) | Committed | Completions | 19/20: 39; 20/21: 48; 21/22: 39; 22/23: 6 | 126
|  |  | VALP expected delivery rate | 19/20: 39; 20/21: 40; 21/22: 46
D-AGT2 | South West of Aylesbury (Hartwell) |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2024/25: 60; 2025/26: 100; 2026/27: 120; 2027/28: 180; 2028/29: 180; 2029/30: 180; 2030/31: 180; 2031/32: 180; 2032/33: 120
| Lower Road Stoke Mandeville (190 dwellings) | Committed | Completions | 18/19: 68; 19/20: 61; 20/21: 58; 21/22: 3 | 190
|  |  | VALP expected delivery rate | 18/19: 68; 19/20: 61; 20/21: 40; 21/22: 21
D-AGT3 | Aylesbury North of A41 (Woodlands) | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2024/25: 30; 2025/26: 120; 2026/27: 120; 2027/28: 120; 2028/29: 120; 2029/30: 120; 2030/31: 120; 2031/32: 120; 2032/33: 120
| Westonmead Farm (157 dwellings) | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 60; 2024/25: 60; 2025/26: 37
| College Farm (250 dwellings) and Manor Farm (350 dwellings) |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2026/27: 75; 2027/28: 160; 2028/29: 160; 2029/30: 160; 2030/31: 45
D-AGT4 | Aylesbury South of A41 (Hampden Fields) |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 80; 2024/25: 150; 2025/26: 225; 2026/27: 300; 2027/28: 300; 2028/29: 300; 2029/30: 300; 2030/31: 300; 2031/32: 300; 2032/33: 300
| Land east of New Road, Weston Turville (WTV020) (64 dwellings) | Committed | Completions | 18/19: 11; 19/20: 53 | 64
VALP expected delivery rate
| Land Bounded by New Road and Aston Clinton Road (WTV025) (135 dwellings) | Committed | Completions | 17/18: 41; 18/19: 47; 19/20: 47 | 135
VALP expected delivery rate
| Land at New Road, Weston Turville (WTV021) (51 dwellings) |  | Completions | [23 empty] | 0
| Land To The South Of Aston Clinton Road, Weston Turville (121 dwellings) |  | Completions | 22/23: 97 | 0
| Both above sites combined |  | VALP expected delivery rate | 22/23: 20; 23/24: 50; 2024/25: 38; 2025/26: 26; 2026/27: 25
D-AGT5 | Berryfields | Committed | Completions | 10/11: 22; 11/12: 164; 12/13: 273; 13/14: 322; 14/15: 455; 15/16: 287; 16/17: 317; 17/18: 266; 18/19: 340; 19/20: 191; 20/21: 92; 21/22: 136; 22/23: 158 | 3023
|  |  | VALP expected delivery rate | 13/14: 321; 14/15: 450; 15/16: 288; 16/17: 317; 17/18: 265; 18/19: 340; 19/20: 191; 20/21: 150; 21/22: 125; 22/23: 100; 23/24: 75; 2024/25: 37
D-AGT6 | Kingsbrook | Committed | Completions | 16/17: 90; 17/18: 221; 18/19: 181; 19/20: 204; 20/21: 184; 21/22: 235; 22/23: 201 | 1316
|  |  | VALP expected delivery rate | [6 empty] | 92 | 219 | 181 | 204 | 150 | 200 | 200 | 200 | 200 | 200 | 154 | 150 | 150 | 150
D-AYL032 | Ardenham Lane |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2030/31: 14; 2031/32: 20; 2032/33: 20
D-AYL073 | Land at Thame Road / Leach Road |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2025/26: 18
D-AYL052 | PO Sorting Office, Cambridge Street |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2025/26: 23
D-AYL059 | Land at Junction of Buckingham Street / New Street |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2030/31: 14
D-AYL063 | Hampden House | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 22/23: 40; 23/24: 40; 2024/25: 32
D-AYL068 | Land North of Manor Hospital |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2029/30: 20; 2030/31: 19
D-AYL115 | Rabans Lane | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 15; 2024/25: 50; 2025/26: 50; 2026/27: 50; 2027/28: 35
D-NLV001 | Land South of A421 and East of Whaddon Road, Newton Longville | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 100; 2024/25: 200; 2025/26: 250; 2026/27: 250; 2027/28: 250; 2028/29: 250; 2029/30: 250; 2030/31: 250; 2031/32: 55
D-WHA001 | Shenley Park |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2024/25: 50; 2025/26: 100; 2026/27: 160; 2027/28: 200; 2028/29: 200; 2029/30: 160; 2030/31: 160; 2031/32: 120
D-BUC043 | LandWest of AVDLP allocation BU1 Moreton Road, Buckingham |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 22/23: 10; 23/24: 50; 2024/25: 50; 2025/26: 20
D-BUC046 | Land off Osier Way (S of A421, E of Gawcott Road) |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 30; 2024/25: 100; 2025/26: 120; 2026/27: 100; 2027/28: 70
D-HAD007 | Land north of Rosemary Lane | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 53; 2024/25: 75; 2025/26: 75; 2026/27: 70
D-HAL003 | RAF Halton |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2024/25: 25; 2025/26: 100; 2026/27: 125; 2027/28: 125; 2028/29: 125; 2029/30: 125; 2030/31: 125; 2031/32: 125; 2032/33: 125
D-WIN001 | Land to East of B4033, Great Horwood |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 55; 2024/25: 85; 2025/26: 80; 2026/27: 40; 2027/28: 40; 2028/29: 15
D-STO008 | Land south of Creslow Way, Stone |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 15; 2024/25: 11
D-WHI009 | Holt's Field, Whitchurch | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 21/22: 10; 22/23: 12
D-CDN001 | Land north of Aylesbury Road and rear of Great Stone House | Committed | Completions | 20/21: 7; 21/22: 0; 22/23: 1 | 7
|  |  | VALP expected delivery rate | 21/22: 8
D-CDN003 | Dadbrook Farm |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2025/26: 10; 2026/27: 5
D-ICK004 | Land off Turnfield | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 21/22: 10; 22/23: 20
D-MMO006 | Land East of Walnut Drive and west of Foscote Road | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 23/24: 25; 2024/25: 40; 2025/26: 40; 2026/27: 40; 2027/28: 25
D-NLV005 | Land S of Whaddon Road and W of Lower Road | Committed | Completions | 22/23: 17 | 0
|  |  | VALP expected delivery rate | 2024/25: 17
D-QUA001 | Land SW of 62 Station Road | Committed | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 22/23: 13
D-QUA0014-016 | Land adjacent to Station Road, Quainton |  | Completions | [23 empty] | 0
|  |  | VALP expected delivery rate | 2025/26: 12; 2026/27: 12
| Year Totals |  |  | 10/11: 22; 11/12: 164; 12/13: 273; 13/14: 643; 14/15: 905; 15/16: 575; 16/17: 816; 17/18: 1012; 18/19: 1236; 19/20: 1090; 20/21: 769; 21/22: 833; 22/23: 895
Note 1: AGT5 Redline on 03/02386/AOP on Uniform dated 13/09/06 confirms Berryfields House (235) and Berryfields Cottage (19) completions are excluded from the 3000. These are therefore excluded from the above completions totals.
Note 2: AGT5 EEH annual report is 3353 total. Does not include 81 on 18/03765/AOP but does include 235 at Berryfields House.
Note 3: D-AYL068 50 gross (44 net) dwellings on part of this site already delivered 2017/18 Reference 16/02051/ADP.
| Allocation delivery in VALP trajectory |  | Total VALP expected delivery rates | 20/21: 380; 21/22: 420; 22/23: 415
| Actual completions from allocations |  | Actual delivery rate from allocations | 20/21: 389; 21/22: 413; 22/23: 480